## WL3001
|  | Plant no: | WL3001 |  |  | Strategy Key
|  | Make/Model | Cat 992K |  |  | PM | Preventative Maintenance |  |  |  |  | HOME
|  | Serial Number | ZMX00442 |  |  | RTF | Run to Failure
|  | Total Meter Reading | 40227 | hours |  | CB | Condition Based | [5 empty] | DATE UPDATED | 2022-08-05
|  | Old Meter reading |  | hours
|  | Current SMU Reading: | 40227 | hours |  |  | Within normal parameter
|  | Date of Reading: | 2025-06-16 |  |  |  | Within 90 Days
|  | Average hours per mth | 400 |  |  |  | Overdue
|  | Labour Cost | 135 | per hour
|  | Warning Lead Time | 90 | days | Warning Lead Date: |  |  | 2025-09-14 | [6 empty] | Cost Forecast | [23 empty] | Man Hours
Item | Component | Strategy | Life Cycle | Hours At Installation | Last Done Date | Life Lived | Hours to Run | Days to Run | Due SMU | Due Date | % Life Completed |  |  |  | 2012-01-01 | 2012-02-01 | 2012-03-03 | 2012-04-03 | 2012-05-04 | 2012-06-04 | 2012-07-05 | 2012-08-05 | 2012-09-05 | 2012-10-06 | 2012-11-06 | 2012-12-07 | 2013-01-07 | 2013-02-07 | 2013-03-10 | 2013-04-10 | 2013-05-11 | 2013-06-11 | 2013-07-12 | 2013-08-12 | 2013-09-12 | 2013-10-13 | 2013-11-13 | 2013-12-14 | 2012-01-01 | 2012-02-01 | 2012-03-03 | 2012-04-03 | 2012-05-04 | 2012-06-04 | 2012-07-05 | 2012-08-05 | 2012-09-05 | 2012-10-06 | 2012-11-06 | 2012-12-07 | 2013-01-07 | 2013-02-07 | 2013-03-10 | 2013-04-10 | 2013-05-11 | 2013-06-11 | 2013-07-12 | 2013-08-12 | 2013-09-12 | 2013-10-13 | 2013-11-13 | 2013-12-14
ENGINE
1 | ENGINE PRIMARY | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
2 | P1 TURBO | PM | 9000 | 34842 | 2023-05-01 | 5385 | 3615 | 271.125 | 43842 | 2026-03-14 03:00 | 59.8333
3 | P2 TURBO | PM | 9000 | 34842 | 2023-05-01 | 5385 | 3615 | 271.125 | 43842 | 2026-03-14 03:00 | 59.8333
3 | FUEL INJECTORS | PM | 9000 | 34842 | 2023-05-01 | 5385 | 3615 | 271.125 | 43842 | 2026-03-14 03:00 | 59.8333
4 | WATER PUMP | PM | 9000 | 34842 | 2023-05-01 | 5385 | 3615 | 271.125 | 43842 | 2026-03-14 03:00 | 59.8333
4 | FUEL COOLER | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
4 | RADIATOR | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
5 | AFTERCOOLER | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
MACHINE ELECTRICAL
6 | ALTERNATOR | RTF | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
7 | EP - STARTER MOTOR | RTF | 9000 | 34842 | 2023-05-01 | 5385 | 3615 | 271.125 | 43842 | 2026-03-14 03:00 | 59.8333
8 | ENGINE WIRING HARNESS | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
9 | TRANSMISSION WIRING HARNESS | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
10 | MACHINE WIRING HARNESS. | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
HYDRAULIC SYSTEM
11 | BUCKET CYLINDER LH | CB | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
12 | BUCKET CYLINDER RH | CB | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
13 | BUCKET TILT CYLINDER | CB | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
14 | HYDRAULIC CONTROL VALVE | CB | 20000 |  |  | 40227 | -20227 | -1517.025 | 20000 | 2021-04-20 23:24 | 201.135
15 | HYDRAULIC PUMPS IMPLEMENT | PM | 12000 | 34842 | 2023-05-01 | 5385 | 6615 | 496.125 | 46842 | 2026-10-25 03:00 | 44.875
16 | HYDRAULIC FAN PUMP | PM | 12000 | 34842 | 2023-05-01 | 5385 | 6615 | 496.125 | 46842 | 2026-10-25 03:00 | 44.875
STEERING SYSTEM
17 | STEERING CYLINDER LH | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
18 | STEERING CYLINDER RH | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
19 | STEERING VALVE | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
19 | STEERING PUMP STR, SECOND, PILOT | PM | 14000 | 34842 | 2023-05-01 | 5385 | 8615 | 646.125 | 48842 | 2027-03-24 03:00 | 38.4643
CAB AND ACCESSORIES
20 | OPERATORS SEAT | CB | 8000 | 34842 | 2023-05-01 | 5385 | 2615 | 196.125 | 42842 | 2025-12-29 03:00 | 67.3125
21 | REFURBISHMENT - PAINT AND SANDBLAST | CB | 30000 | 34842 | 2023-05-01 | 5385 | 24615 | 1846.125 | 64842 | 2030-07-06 03:00 | 17.95
22 | AIR CONDITIONER COMPRESSOR | RTF | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
23 | AIR CONDITIONER CONDENSOR | RTF | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
24 | AIR CONDITIONER EVAPORATOR | RTF | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
FRAME AND BODY
25 | FRAME | CB | 30000 |  |  | 40227 | -10227 | -767.025 | 30000 | 2023-05-10 23:24 | 134.09
26 | ARTIC HITCH REBUILD | CB | 20000 |  |  | 40227 | -20227 | -1517.025 | 20000 | 2021-04-20 23:24 | 201.135
27 | BUCKET REBUILD MAJOR | CB | 15000 |  |  | 40227 | -25227 | -1892.025 | 15000 | 2020-04-10 23:24 | 268.18
28 | BOOM REPAIR - MAJOR | CB | 20000 |  |  | 40227 | -20227 | -1517.025 | 20000 | 2021-04-20 23:24 | 201.135
29 | TILT LINK REPAIR - MAJOR | CB | 20000 |  |  | 40227 | -20227 | -1517.025 | 20000 | 2021-04-20 23:24 | 201.135
POWER TRAIN
30 | TRANSMISSION | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
31 | TRANSMISSION PUMP | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
31 | TRANSMISSION COOLER | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
32 | TORQUE CONVERTER | PM | 18000 | 36316 | 2024-02-01 | 3911 | 14089 | 1056.675 | 54316 | 2028-05-07 16:12 | 21.7278
32 | TORQUE CONVERTER VALVE & LINES | PM | 18000 | 34842 | 2023-05-01 | 5385 | 12615 | 946.125 | 52842 | 2028-01-18 03:00 | 29.9167
33 | DRIVE SHAFT | PM | 20000 |  |  | 40227 | -20227 | -1517.025 | 20000 | 2021-04-20 23:24 | 201.135
34 | DIFF OSCILATOR | PM | 20000 |  |  | 40227 | -20227 | -1517.025 | 20000 | 2021-04-20 23:24 | 201.135
AXLE GP
35 | DIFFERENTIAL - FRONT | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
36 | DIFFERENTIAL - REAR | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
37 | DIFF OSCILATOR | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
37 | POS 1 - FINAL DRIVE | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
38 | POS 2 - FINAL DRIVE | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
39 | POS 3 - FINAL DRIVE | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
40 | POS 4 - FINAL DRIVE | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
41 | BRAKE PUMP | PM | 15000 | 34842 | 2023-05-01 | 5385 | 9615 | 721.125 | 49842 | 2027-06-07 03:00 | 35.9
42 | POS 1 - BRAKES | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
43 | POS 2 - BRAKES | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
44 | POS 3 - BRAKES | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
45 | POS 4 - BRAKES | PM | 20000 | 34842 | 2023-05-01 | 5385 | 14615 | 1096.125 | 54842 | 2028-06-16 03:00 | 26.925
SERVICE EQUIPMENT
46 | Pos 1 Rim OTC6121 | PM | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
47 | Pos 2 Rim OTC6124 | PM | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
46 | Pos 3 Rim OTC6123 | PM | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
48 | Pos 4 Rim OTC4943 | PM | 10000 | 34842 | 2023-05-01 | 5385 | 4615 | 346.125 | 44842 | 2026-05-28 03:00 | 53.85
[15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on E55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed at 36316hrs, 1/2/2024, Macmahon had fitted T/C and was replaced under warranty at 36316hrs C:\Users\JonothanDark\Worx Equipment\Operations - Asset Register\WL3001 - Cat 992K Loader\Major Component History\WL3001 Torque Convertor Failure Original hrs of TC change 34842 - 1/5/2023